## projetos
Projeto | Descrição | Orçamento | Data Aprovação | Data de Conclusão | Data Última Atualização | Status | Gerente Projeto | Equipe | Horas Trabalhadas
PROJ-20-3000 | Manutenção Motores | 620000 | 2020-01-10 | 2020-12-25 | 2020-12-30 | Finalizado | Mauricio L. | 5 | 12000
PROJ-20-3001 | Manutenção Paineis | 500000 | 2020-01-05 | 2020-12-25 | 2020-12-30 | Finalizado | Gustavo A. | 8 | 19200
PROJ-20-3002 | Manutenção Embarcação | 1010000 | 2020-01-20 | 2020-12-25 | 2020-12-30 | Finalizado | Alice B. | 4 | 9600
PROJ-20-3003 | Manutenção Galpão | 372000 | 2020-01-10 | 2020-12-18 | 2020-12-30 | Finalizado | Bianca G. | 6 | 14400
PROJ-20-3004 | Manutenção Máquinas | 270000 | 2020-01-05 | 2020-12-18 | 2020-12-30 | Finalizado | Alice B. | 6 | 14400
PROJ-20-3005 | Manutenção Engrenagens | 336000 | 2020-01-05 | 2020-12-18 | 2020-12-30 | Finalizado | Bianca G. | 3 | 7200
PROJ-20-3006 | Manutenção de Softwares | 240000 | 2020-01-02 | 2020-12-18 | 2020-12-30 | Finalizado | Gustavo A. | 4 | 48000

## orcamento_projeto
Projeto | Descrição | 2020-01-01 | 2020-02-01 | 2020-03-01 | 2020-04-01 | 2020-05-01 | 2020-06-01 | 2020-07-01 | 2020-08-01 | 2020-09-01 | 2020-10-01 | 2020-11-01 | 2020-12-01
PROJ-20-3000 | Manutenção Motores | 12400 | 6200 | 12400 | 31000 | 31000 | 62000 | 93000 | 124000 | 155000 | 49600 | 31000 | 12400
PROJ-20-3001 | Manutenção Paineis | 5000 | 10000 | 15000 | 50000 | 50000 | 75000 | 50000 | 90000 | 105000 | 35000 | 10000 | 5000
PROJ-20-3002 | Manutenção Embarcação | 50500 | 50500 | 10100 | 101000 | 202000 | 303000 | 121200 | 50500 | 50500 | 20200 | 20200 | 30300
PROJ-20-3003 | Manutenção Galpão | 7440 | 3720 | 7440 | 18600 | 18600 | 37200 | 55800 | 74400 | 93000 | 29760 | 18600 | 7440
PROJ-20-3004 | Manutenção Máquinas | 27000 | 13500 | 27000 | 54000 | 54000 | 40500 | 21600 | 13500 | 5400 | 5400 | 5400 | 2700
PROJ-20-3005 | Manutenção Engrenagens | 33600 | 16800 | 33600 | 67200 | 67200 | 50400 | 26880 | 16800 | 6720 | 6720 | 6720 | 3360
PROJ-20-3006 | Upgrade de Sistemas | 4800 | 2400 | 4800 | 12000 | 12000 | 24000 | 36000 | 48000 | 60000 | 19200 | 12000 | 4800

## custo_projeto
Período | Valor | Moeda | Descricao do Item | PROJETO | Classificação | Fornecedor
2020-01-01 | 15000 | BRL | ENGINE PARTs | PROJ-20-3000 | MATERIAL | SOFTX COMPANY
2020-02-01 | 4000 | BRL | ENGINE PARTs | PROJ-20-3000 | MATERIAL | SOFTX COMPANY
2020-03-01 | 20000 | BRL | ENGINE PARTs | PROJ-20-3000 | MATERIAL | SOFTX COMPANY
2020-04-01 | 50000 | BRL | Engineering Services | PROJ-20-3000 | SERVIÇO | CAYG Engineering
2020-05-01 | 50000 | BRL | Engineering Services | PROJ-20-3000 | SERVIÇO | CAYG Engineering
2020-06-01 | 120000 | BRL | Engineering Services | PROJ-20-3000 | SERVIÇO | CAYG Engineering
2020-07-01 | 10000 | BRL | Spare Parts | PROJ-20-3000 | MATERIAL | SOFTX COMPANY
2020-08-01 | 200000 | BRL | Engineering Services | PROJ-20-3000 | SERVIÇO | CAYG Engineering
2020-09-01 | 155000 | BRL | Engineering Services | PROJ-20-3000 | SERVIÇO | CAYG Engineering
2020-10-01 | 120000 | BRL | Panel Mounting and System Structure | PROJ-20-3000 | MATERIAL | SOFTX COMPANY
2020-01-01 | 4500 | BRL | Panel Mounting Structure | PROJ-20-3001 | MATERIAL | SOFTX COMPANY
2020-02-01 | 9000 | BRL | Local Labor | PROJ-20-3001 | SERVIÇO | LABOR
2020-03-01 | 13500 | BRL | Databook Registration | PROJ-20-3001 | OUTROS | HUSR Certification
2020-04-01 | 60000 | BRL | Onsite Survey | PROJ-20-3001 | MATERIAL | VESSEL D&A CO
2020-05-01 | 60000 | BRL | Equipment & Tools | PROJ-20-3001 | MATERIAL | VESSEL D&A CO
2020-06-01 | 67500 | BRL | Equipment & Tools | PROJ-20-3001 | SERVIÇO | CAYG Engineering
2020-07-01 | 45000 | BRL | Maitenance Execution | PROJ-20-3001 | SERVIÇO | CAYG Engineering
2020-08-01 | 81000 | BRL | Maitenance Execution | PROJ-20-3001 | SERVIÇO | CAYG Engineering
2020-09-01 | 94500 | BRL | Maitenance Execution | PROJ-20-3001 | SERVIÇO | CAYG Engineering
2020-10-01 | 31500 | BRL | Maitenance Execution | PROJ-20-3001 | SERVIÇO | CAYG Engineering
2020-01-01 | 106050 | BRL | Materials and Spare | PROJ-20-3002 | MATERIAL | VESSEL D&A CO
2020-02-01 | 9000 | BRL | Survey | PROJ-20-3002 | SERVIÇO | VESSEL D&A CO
2020-03-01 | 65000 | BRL | General Maitenance | PROJ-20-3002 | SERVIÇO | VESSEL D&A CO
2020-04-01 | 106050 | BRL | General Maitenance | PROJ-20-3002 | SERVIÇO | VESSEL D&A CO
2020-05-01 | 212100 | BRL | General Maitenance | PROJ-20-3002 | SERVIÇO | VESSEL D&A CO
2020-06-01 | 293910 | BRL | General Maitenance | PROJ-20-3002 | SERVIÇO | VESSEL D&A CO
2020-07-01 | 117564 | BRL | General Maitenance | PROJ-20-3002 | SERVIÇO | VESSEL D&A CO
2020-08-01 | 48985 | BRL | General Maitenance | PROJ-20-3002 | SERVIÇO | VESSEL D&A CO
2020-09-01 | 48985 | BRL | General Maitenance | PROJ-20-3002 | SERVIÇO | VESSEL D&A CO
2020-10-01 | 9797 | BRL | General Maitenance | PROJ-20-3002 | SERVIÇO | VESSEL D&A CO
2020-01-01 | 14880 | BRL | General Maitenance | PROJ-20-3003 | SERVIÇO | CAYG Engineering
2020-02-01 | 18600 | BRL | General Maitenance | PROJ-20-3003 | SERVIÇO | CAYG Engineering
2020-03-01 | 22320 | BRL | General Maitenance | PROJ-20-3003 | SERVIÇO | CAYG Engineering
2020-04-01 | 33480 | BRL | General Maitenance | PROJ-20-3003 | SERVIÇO | CAYG Engineering
2020-05-01 | 18600 | BRL | Spare Parts | PROJ-20-3003 | MATERIAL | SOFTX COMPANY
2020-06-01 | 37200 | BRL | Spare Parts | PROJ-20-3003 | MATERIAL | SOFTX COMPANY
2020-07-01 | 55800 | BRL | General Maitenance | PROJ-20-3003 | SERVIÇO | CAYG Engineering
2020-08-01 | 74400 | BRL | General Maitenance | PROJ-20-3003 | SERVIÇO | CAYG Engineering
2020-09-01 | 120000 | BRL | General Maitenance | PROJ-20-3003 | SERVIÇO | CAYG Engineering
2020-10-01 | 29760 | BRL | General Maitenance | PROJ-20-3003 | SERVIÇO | CAYG Engineering
2020-01-01 | 24300 | BRL | Materials and Spare | PROJ-20-3004 | MATERIAL | CAYG Engineering
2020-02-01 | 12150 | BRL | Materials and Spare | PROJ-20-3004 | MATERIAL | CAYG Engineering
2020-03-01 | 24300 | BRL | Materials and Spare | PROJ-20-3004 | MATERIAL | CAYG Engineering
2020-04-01 | 48600 | BRL | General Maitenance | PROJ-20-3004 | SERVIÇO | CAYG Engineering
2020-05-01 | 48600 | BRL | General Maitenance | PROJ-20-3004 | SERVIÇO | CAYG Engineering
2020-06-01 | 36450 | BRL | General Maitenance | PROJ-20-3004 | SERVIÇO | CAYG Engineering
2020-07-01 | 19440 | BRL | General Maitenance | PROJ-20-3004 | SERVIÇO | CAYG Engineering
2020-08-01 | 12150 | BRL | General Maitenance | PROJ-20-3004 | SERVIÇO | CAYG Engineering
2020-09-01 | 4860 | BRL | Project Documentation | PROJ-20-3004 | SERVIÇO | CAYG Engineering
2020-10-01 | 10000 | BRL | Project Documentation | PROJ-20-3004 | SERVIÇO | CAYG Engineering
2020-01-01 | 30240 | BRL | ENGINE PARTs | PROJ-20-3005 | MATERIAL | SOFTX COMPANY
2020-02-01 | 15120 | BRL | ENGINE PARTs | PROJ-20-3005 | MATERIAL | SOFTX COMPANY
2020-03-01 | 30240 | BRL | ENGINE PARTs | PROJ-20-3005 | MATERIAL | SOFTX COMPANY
2020-04-01 | 60480 | BRL | General Maitenance | PROJ-20-3005 | SERVIÇO | CAYG Engineering
2020-05-01 | 60480 | BRL | General Maitenance | PROJ-20-3005 | SERVIÇO | CAYG Engineering
2020-06-01 | 45360 | BRL | Engineering Services | PROJ-20-3005 | SERVIÇO | CAYG Engineering
2020-07-01 | 24192 | BRL | Spare Parts | PROJ-20-3005 | MATERIAL | SOFTX COMPANY
2020-08-01 | 15120 | BRL | Engineering Services | PROJ-20-3005 | SERVIÇO | CAYG Engineering
2020-09-01 | 15120 | BRL | Engineering Services | PROJ-20-3005 | SERVIÇO | CAYG Engineering
2020-10-01 | 7500 | BRL | Engineering Services | PROJ-20-3005 | SERVIÇO | SOFTX COMPANY
2020-01-01 | 4896 | BRL | Onsite Survey | PROJ-20-3006 | SERVIÇO | REX POWER
2020-02-01 | 2448 | BRL | Onsite Survey | PROJ-20-3006 | SERVIÇO | REX POWER
2020-03-01 | 4896 | BRL | Onsite Survey | PROJ-20-3006 | SERVIÇO | REX POWER
2020-04-01 | 12240 | BRL | Equipment Manufacturing Tools | PROJ-20-3006 | MATERIAL | REX POWER
2020-05-01 | 12240 | BRL | Equipment Manufacturing Tools | PROJ-20-3006 | MATERIAL | REX POWER
2020-06-01 | 19200 | BRL | Equipment Manufacturing Tools | PROJ-20-3006 | MATERIAL | REX POWER
2020-07-01 | 28800 | BRL | Engineering Services | PROJ-20-3006 | SERVIÇO | REX POWER
2020-08-01 | 38400 | BRL | Engineering Services | PROJ-20-3006 | SERVIÇO | REX POWER
2020-09-01 | 48000 | BRL | Systems implementation | PROJ-20-3006 | SERVIÇO | REX POWER
2020-10-01 | 50000 | BRL | Systems implementation | PROJ-20-3006 | SERVIÇO | REX POWER
2020-11-01 | 5000 | BRL | Maitenance Execution | PROJ-20-3001 | SERVIÇO | CAYG Engineering
2020-12-01 | 10000 | BRL | Maitenance Execution | PROJ-20-3001 | SERVIÇO | CAYG Engineering
2020-12-01 | 9797 | BRL | General Maitenance | PROJ-20-3002 | SERVIÇO | VESSEL D&A CO
2020-12-01 | 10000 | BRL | General Maitenance | PROJ-20-3003 | SERVIÇO | CAYG Engineering
2020-12-01 | 5000 | BRL | Project Documentation | PROJ-20-3004 | SERVIÇO | CAYG Engineering
2020-11-01 | 7500 | BRL | Engineering Services | PROJ-20-3005 | SERVIÇO | SOFTX COMPANY
2020-12-01 | 10000 | BRL | Engineering Services | PROJ-20-3005 | SERVIÇO | SOFTX COMPANY
2020-11-01 | 15000 | BRL | Systems implementation Report | PROJ-20-3006 | SERVIÇO | REX POWER